## Introduction
This is the Project Tracker
You will use this to track your work on your project. The first step is to identify your team on the Team sheet. Also on the Team Sheet, you will specify the address of your GitHub repository for the project. After that, you will complete the Features sheet, which is a summarized version of the use cases you wrote for the last assignment. In addition to listing summary versions of your use cases, recall that you also listed in your Business Requirements document various resources users will need to use your product, so include as "features" the task of creating such resources so you can allocate time to making them.
Then you will identify, in helpful detail, the tasks you will perform to implement each feature. You have to be detailed here, thinking very clearly about what it will take to pursue each task in terms of time.
AFter that, on the Test Plans sheet, you will describe how you will test that each feature is working. Finally, on the Work Log tab, you will enter entries for each work session you spend building your project. Include links to particular assets in your GitHub respository that I can refer to to see evidence of your work.
The purpose of this sheet is to serve as a guide and a tracking mechanism as you try to build the various features of your project.

## Team
Team Members
Team member name | Email address
Caleb okrzesik | calebmokrzesik@lewisu.edu
Project GitHub | https://github.com/CalebOkrzesik/capstoneprojects
Just list the names and email addresses of the members that comprise this team. If there is only one person, just specify one name and email address.

## Features
Feature List
Feature ID | Feature Name | Feature Description
NA-1 | Photo Storage | Photo backup and storage from anywhere like google photos
NA-2 | Movie Streaming | Streaming of Movies and TV for free like Netflix
NA-3 | Storage/NAS | Storage Backup like google drive
CA-1 | Home Automation App | Home automation features (Lighting, speaker control, and TVs)
CA-2 | Host Website | Run my website off It instead of GitHub(I coded it myself)
CA-3 | Wheather App | App that I can check local Wheather on
CA-4 | sudko | Will allows game play as well as AI Solving
VM-1 | Runs linux | VM to run Linux ISO
VM-2 | Runs Windows | VM to run Windows
NA | Native App | One that is pre-made for me to run on trueNas but requires setup
CA | Custom App | One that I coded from scratch
VM | Virtual Machine | Different Virtual Machines
Complete
Not Started
Working On
Here we list the specific features of your final project. This is just an alternative way to express what you did for the last assignment. Features are the things your project offers the user, so focus on what the user will experience. What will the user be able to do? How will they interact with what you are building? What will they see when they use what you are building?
For each feature, specify a Feature ID. Perhaps this is just a number, or maybe its a short abbreviation that you'll use to uniquely identify each feature. Then specify a name for the feature that describes cleaerly what it concerns. Finally, offer a very specific but brief description. You already did this in the preceding assignment, but if you weren't specific there, you need to be specific here. Otherwise, you can copy the use case text you wrote in that last assignment. The description you provide here should give us a clear understanding of what the user will be able to do and see and interact with in your product.

## Task Estimation
Task Estimation
Feature ID | Task ID | Task Name | Task Description | Estimated Hours | ID of tasks this depends on | Assigned team members | Complete
NA-1 | T-1 | Photo Storage | Use TrueNas to Create the App and use reverse proxy to allow Access outside the home | 4 | N/A | Caleb | Yes
NA-2 | T-2 | Movie Streaming | Use TrueNas to Create the App | 5 | N/A | Caleb | Yes
NA-3 | T-3 | Storage/NAS | Use TrueNas to Create the App | 2 | N/A | Caleb | Yes
CA-1 | T-4 | Home Automation App | Use Code that works best for this to create a working app and implment it on the sever | 20 | N/A | Caleb | No
CA-2 | T-5 | Host Website | Use Code that works best for this to create a working app and implment it on the sever | 4 | N/A | Caleb | No
CA-3 | T-6 | Wheather App | Use Code that works best for this to create a working app and implment it on the sever | 25 | N/A | Caleb | No
CA-4 | T-7 | sudko | Use Code that works best for this to create a working app and implment it on the sever | 30 | N/A | Caleb | No
VM-1 | T-8 | Runs linux | Use Severs Built in VM runner to run Virtual Machine | 2 | N/A | Caleb | No
VM-2 | T-9 | Runs Windows | Use Severs Built in VM runner to run Virtual Machine | 1 | N/A | Caleb | No
93
Priority
High
Medium
Low
Here we list the tasks you estimate will be needed to complete your project (in other words, to implement its features). Each row represents a task.
For each task, specify the ID of the corresponding feature. These should come from the list of features you provided on the Features sheet, so perhaps use an Excel formula to set them. Then specify the ID of this task. Perhaps it's just a number, or maybe it's an abbreviation, or maybe it's a combination of the feature ID and a number or a letter - for example, if the feature ID is 1 and you want to represent that this is the first task for implementing feature 1, perhaps you could set the Task ID as 1.1 or 1.A.
Next, specify a Task Name. It should clearly but briefly describe what this task concerns.
Next, describe clearly what is needed to accomplish this task. What steps will you take to carry it out
Then specify how many hours it will take to complete the task. This is just an estimate at this point. If this task depends on another task being done, indicate the task ID of the task it depends on in the next column. Finally, specify who is responsible for completing the task. This could be multiple team members if two or more people are needed to complete the task.
Make sure you in include in your time estimate for each task some time for testing that the task was done correctly / is producing the right output. A good rule of thumb is to allot an additional amount of about 20% to 25% of the time it took to do a task for testing that it works. You won't be testing every single task, and the test plans on the test plans sheet will connect to the overall features rather than the individual tasks. Nevertheless, if you follow the rule of thumb that 20% to 25% of your work effort should be added for testing, you will be sure to allow the right amount of time for it.

## Test Plans
Test plans
Feature ID | Test ID | Test Name | Test Description | Tester | Successful outcome
NA-1 | TI-1 | View/Update Photos | Check for the ability to Download/Upload/View/Change Images | Caleb | Complete All 4 Test without Fail consistently
NA-2 | TI-2 | Watch Movie | Watch a full movie without any glitches | Caleb | Full Movie Played No Glitches
NA-3 | TI-3 | Upload/Download | Upload file and download to sever | Caleb | File upload download completed without Fail
CA-1 | TI-4 | Lights and TV Power Control | App allows for TV and Lights Power on off | Caleb | Lights and TV Turn on/off
CA-2 | TI-5 | Website Connection | Try to connect to website while at Home and externally | Caleb | Can access website from anywhere
CA-3 | TI-6 | Check Wheather | Check the wheather for the current area for accurary and compare it to app | Caleb | Wheather is the same in app as elsewhere
CA-4 | TI-7 | Play Game | Play the game and look for bugs | Caleb | The game loop runs with no bugs
VM-1 | TI-8 | Run Linux VM | Run the linux virtual machine to test for stability | Caleb | Runs stabily
VM-2 | TI-9 | Run Winows VM | Run the windows virtual machine to test for stability | Caleb | Runs stabily
Caleb
Caleb
Caleb
Caleb
Caleb
Caleb
Caleb
On this sheet, describe how you will test each feature. Each row represents a test you will conduct. You might have multiple tests for each feature to confirm that that feature is working.
In the first column, specify the ID of the feature listed on the Features sheet that this test corresponds to.
In the Test ID column, give this test a unique id. Perhaps it is a combination of the feature ID and a number or letter or abbreviation for this particular test. For example, if the related feature is ID # 1, and this is the first test for ID #1, perhaps the test ID should be 1.1 or 1.A. But you can choose your own unique id system.
In the Test Name column, specify a clear, concise name for this test.
In the Test Description column, specify a clear, concise, but complete description of how the test will be conducted.
In the Tester column, indicate the names of the people on the team who will conduct the test.
Finally, in the Successful Outcome column, describe how you will know that your work passed this test. In other words, how will know that your work successfully implemented the feature it supports?

## Work Log
Task ID (from Task Estimation Sheet) | Date the work was done | Time spent (hours) | Work done by whom? | Description of what was done (be claar in describing the work you did. A step-by-step description would be good.) | Document on GitHub that provides more detail about what was accomplished through this task.
T-1 | 2025-09-15 | 4 | Caleb | Created storage space on sever for apps data. Then created app through TrueNas. After that setup tailscale so I could do a reverse proxy and allowsaccesiblity from anywhere. So basicallly ip setup. After that I Setup the app side and web side of the sever. | https://github.com/CalebOkrzesik/capstoneprojects/blob/main/ImmichPhotosApp.docx
T-2 | 2025-09-26 | 5 | Caleb | Created storage space on sever for apps data. Created app by using TrueNas built in function. Then I setup up the IP. Next I started uploading my media to the sever. The play back I had to trouble shoot a lot but in the end I relized I just needed more bandwith so I plugged in eathernet cable to my tv. There is an app that allows you to wacth on any device from your sever. | https://github.com/CalebOkrzesik/capstoneprojects/blob/main/JellyFinMoviesApp.docx
T-3 | 2025-09-08 | 2 | Caleb | This part was pretty easy. I Just configure the storage in the NAS with TrueNas. First step was to allocate storage to mirror the data between my 2 3tb drives. Then I set up security for the server and data on it with enceryption ect. Then I made a storage pool and this is accessable on the home network as a storage device. | https://github.com/CalebOkrzesik/capstoneprojects/blob/main/NasServerSetup.docx
T-4
T-5
T-6
T-7
T-8
T-9